## SAGT V2.0
SAGT
S.No. | Critical Activities | Date to commence | Target Date | Remarks/Progress | Responsibility
1 | Integration related | 13.12.2018 | 21.12.2018
1.1 | Modification required for new report development and Field mapping for LCM cost |  |  | SOA consultant | Rajendra, Amila
1.2 | LCM (integration between EBS and Fusion) |  |  | Development is completed. | Rajendra, Amila
1.3 | Invoice & Credit notes (Integration between NAVIS and Fusion) (SR Created) | 13.12.2018 | 14.12.2018 | SOA consultant, credit note & credit note application, memo line & mapping set creation for related party customer. Transaction type mapping , | Rajendra, Amila
1.4 | Customer Creation (Integration between NAVIS and Fusion) |  |  | SOA consultant | Rajendra, Amila
1.5 | Ananlysis of current NAVIS integration points in order to assertain the effort needed by KPMG, SOA consultant and SAGT |  |  | SOA consultant | Rajendra, Amila
1.6 | Transfer SOA to production |  |  | SOA consultant | Rajendra, Amila
1.7 | CRP 2 ( NAVIS / GRN/ GL _) Demo - |  |  | CRP 2 Completed. Issue in Creidt Memo at Fusion side | SAGT,Amila
1.8 | Get proper documentation and training for SOA integration. |  |  | SOA consultant | Rajendra, Amila
1.9 | AR Receipts methods and mapping | 13.12.2018 | 14.12.2018 | mapping to be done with NAVIS | Amila
2 | Functional Testing on Integration |  |  | Arjuna has to complete all the functional testing related to integration along with Amila. Arjuna has to get confirmation from SAGT. This will be included in UAT. SAGT has to ownership of NAVIS integration | Arjuna
3 | Printer Configuration - Go with printer server or buy another compatible printer |  | 17.12.2018 | This was delayed from SAGT even though Amila was coordinating several times | SAGT,Amila K
4 | Oracle EBS to move to Cloud - NW related issues, Amila K working with Ravin |  | 17.12.2018 | Not Practical to upload directly. Install tool in DBCS and down load | SAGT, Amila
4.1 | Make arrangements to upload the data through SLT link and install EBS in the cloud and the number of days |  | 17.12.2018 | Need to decide the number of days | Amila K
4.2 | EAM Iaas testing |  | 17.12.2018 | Need to confirm the performance | SAGT, Arjuna
5 | Bank Integration (to be checked) as not identified in the scope - (SCB & HSBC) I- File Vs Host to Host |  | 13.12.2018 | Decision taken to implement using I -file. Priyantha/Arjuna to provide format. Sayuru has to deveop a program | Priyantha, Arjuna, Sayuru, Amila
5.1 | I-file testing snd development |  | 14.12.2018 |  | Sayuru
6 | Master Data
6.1 | Master Data (supplier) to be extracted and validate |  | 16.11.2018 | SAGT has validated | SAGT
6.2 | Master Data (Customer) to be extracted and validate |  | 16.11.2018 | SAGT has validated | SAGT
6.3 | Master Data (Inventory) to be extracted and validate | 08.11.2018 | 20.11.2018 | SAGT has to validate | SAGT
6.4 | Master Data (Asset Register) to be confirmed | 09.11.2018 | 20.11.2018 | SAGT has validated | SAGT
6.5 | Master Data (Bank) to be confirmed | 09.11.2018 | 20.11.2018 | SAGT has validated | SAGT
6.6 | Master Data on AR Trnsaction type and Recipts methods | 09.11.2018 | 27.11.2018 | SAGT has sent already. | SAGT
7 | COA with numbering / Asset categories/ |  | 13.12.2018 | Series of discussion held with SAGT to finalise COA. Completed on 14.12.2018 | SAGT, KPMG
8 | Reports Development |  |  | Initially Arjuna confirmed with SAGT for 12 operational reports. Later SAGT added 6 more reports. 3 more ePort reports added | Amila
8.1 AP | SAGT Cheque Payments (Payment Voucher ) | 19.12.2018 | 21.12.2018 |  | Sayuru
8.2 AP | SAGT WHT Schedule |  |  |  | Amila
8.3 AP | SAGT WHT certifcate |  |  |  | Amila
8.4 AP | SAGT Unpaid WHT |  |  | SAGT to provide specification/report output | SAGT
8.5 AP | SAGT Check Printing Program (Print check) | 19.12.2018 | 21.12.2018 |  | Sayuru
8.6 AP | SAGT VAT Return Schedule |  |  | SAGT to provide specification/report output | SAGT
8.7 AR | SAGT Debit/Credit Note Printing | 19.12.2018 | 21.12.2018 |  | Sayuru
8.8 AR | SAGT Debtor Statement Text,Excel and PDF | 19.12.2018 | 21.12.2018 |  | Sayuru
8.9 AR | SAGT AR Receipt print | 19.12.2018 | 21.12.2018 |  | Sayuru
8.10PUR | Purchase Order Print | 19.12.2018 | 21.12.2018 |  | Sayuru
8.11 PUR | Purchase Requisition Print | 19.12.2018 | 21.12.2018 |  | Sayuru
8.12LCM | SAGT LCM Reconciliation Report |  |  |  | Amila
8.13LCM | SAGT LCM Summary Report |  |  |  | Amila
8.14LCM | SAGT LCM Un-matched Estimated Amounts Report |  |  |  | Amila
8.15AP | SAGT receiving accrual value report |  |  |  | Amila
8.16AP | SAGT SVAT FORM 6 |  |  |  | Amila
8.17FA | Assets detail report |  |  |  | Amila
8.18AP | SAGT Tax Register |  |  |  | Amila
8.19 GL | FRS Reports |  |  | Azeem to support | Azeem
8.2 | ePort Report |  |  |  | Amila
8.21 | ePort Report |  |  |  | Amila
8.22 | ePort Report |  |  |  | Amila
8.23 | ePort Report |  |  |  | Amila
9 | Walk thru Session on the Technical Design document and Sign off |  | 16.11.2018 | Second walk through session on Technical Design Document conducted on 14th Dec 2018. SAGT requested some more modifications. | SAGT,Amila
10 | Oracle Fusion administration related training |  |  | Initially planned for 7th and postponed | Arjuna
11 | Re print of cheques (Cheque printing control issue) |  |  | Include in Gap Register and follow the process agreed . To be clarified | Arjuna
12 | Black out period for EAM |  |  | To be informed to SAGT | KPMG
13 | ePort OF related reports |  |  | ePort system from EBS available and need to be querried from Fusion Cloud. This is a new requirement requested by SAGT in Nov 2018. Fahad suggested for online data retrieval we can create a report that can be accessed via Web Service from Fusion based on parameters. The web service authentication is a Fusion Username/password. Fahad has developed a web service. Amila received the report formats. 4 reports to be developed. There will be a discussion with Lakmana on 13.12.2018 | SAGT, Fahad
14 | UAT related |  |  |  | 1mila
14.1 | UAT Scripts | 03.12.2018 | 14.12.2018 | GL, FA, CM AP, Procurement, Inventory & Self Service Procurement sent to SGAT. AR will be sent by 17.12.2018 | Priyantha, Arjuna
14.2 | Prepare open transaction queries for AR, AP & Purchasing, extract and send for confirmation | 17.12.2018 | 18.12.2018 | Amila to support immeduately | Amila
14.3 | Creating UAT Users and Roles | 13.12.2018 | 14.12.2018 |  | Arjuna
14.4 | Setting up UAT instance /Configuration |  |  | Completed | Priyantha, Arjuna, Anas
14.5 | GL Setup | 17.12.2018 | 18.12.2018 |  | Priyantha
14.6 | TB Upload | 18.12.2018 | 18.12.2018 |  | Priyantha
14.7 | GL Internal testing | 18.12.2018 | 19.12.2018 |  | Priyantha
14.8 | Create FRS reports based on FSG Report |  |  |  | Chathumanthi, Azim
14.9 | AP Setup | 18.12.2018 | 19.12.2018 |  | Priyantha
14.1 | Supplier upload | 18.12.2018 | 19.12.2018 |  | Priyantha
14.11 | AP open transactions upload | 20.12.2018 | 21.12.2018 |  | Shehan
14.13 | AP UAT Internal testing | 21.12.2018 | 21.12.2018 |  | Shehan
14.14 | AR Setup | 18.12.2018 | 19.12.2018 |  | Arjuna, Priyantha
14.15 | Customer Upload | 18.12.2018 | 19.12.2018 |  | Roshan
14.16 | AR Open transaction upload | 20.12.2018 | 21.12.2018 |  | Roshan
14.17 | AR UAT Internal testing | 21.12.2018 | 21.12.2018 |  | Arjuna
14.18 | Purchaing, Inventory & LCM setup | 18.12.2018 | 19.12.2018 |  | Maleena, Arjuna
14.19 | Item Master upload | 18.12.2018 | 19.12.2018 |  | Maleena, Arjuna, Shehan
14.2 | Open PO upload | 20.12.2018 | 21.12.2018 |  | Maleena, Arjuna, Shehan
14.21 | Purchasing, Inventory & LCM internal testing | 21.12.2018 | 21.12.2018 |  | Maleena, Arjuna, Shehan
14.22 | CM Setup | 19.12.2018 | 19.12.2018 |  | Priyantha, Arjuna
14.23 | Bank upload | 19.12.2018 | 20.12.2018 |  | Chathumanthi
14.24 | Swift 940 configuration and bank auto reconciliation process | 19.12.2018 | 21.12.2018 |  | Chathumanthi
14.25 | CM Internal testing |  |  |  | Priyantha, Chathumanthi
14.26 | FA Setup |  |  |  | Priyantha, Arjuna,Shehan
14.27 | Asset Register Upload |  |  |  | Priyantha, Arjuna,Shehan
14.28 | FA Internal testing |  |  |  | Priyantha, Arjuna,Shehan
15 | All integrations to be transferred to UAT instance | 19.12.2018 | 20.12.2018 |  | Amila
16 | Conduct UAT | 24.12.2018 | 29.12.2018 |  | Priyantha, Arjuna
16.1 | UAT confirmation and Sign Off | 30.12.2019 | 31.12.2018 |  | KPMG, SAGT
17 | Production configuration in fusion | 30.12.2018 | 05.01.2019 |  | Priyantha, Arjuna
18 | Cutover Data upload & TB upload | 06.01.2019 | 07.01.2019 |  | Priyantha, Arjuna
19 | Transfer EBS production instance to Iaas |  |  |  | Priyantha, Arjuna, Amila
19.1 | Apply pre requiste patches to EBS (Production instance ) | 24.12.2018 | 25.12.2018 | If system outage is there to be informed to SAGT in advance | Amila K
19.2 | EBS Production instance backup upload to cloud storage | 05.01.2019 | 05.01.2019 |  | Amila K
19.3 | Production instance clone by cloud storage backup | 06.01.2019 | 06.01.2019 |  | Amila K
19.4 | Functional tetsing to be done | 06.01.2019 | 06.01.2019 |  | Arjuna, Priyantha
20 | Transfer all Integration to production including NAVIS | 07.01.2019 | 08.01.2019 |  | Amila Silva
22 | Go Live |  | 09.01.2019 |  | KPMG, SAGT